## EXAMPLE TEMPLATE
Land Based Activity Planning Tool
Developed by Meadow Lake Tribal Council Health
1 | Project Name: | Buffalo Harvest |  | Date(s) of event: | XX-XX-2025
2 | Goal of the Project: | engage students in a traditional food harvest; Improve access to local and traditional foods in school
3 | What are the objectives?
plan a pipe ceremony in November to coincide with the first harvest (day before)
harvest 1 buffalo per school during Nov to Dec
work with schools to plan and coordinate dates with local buffalo ranch
work with schools to define the plan for butchering and transporting meat from the field.
4 | What are the activities?
Planning meetings Sept - October with school staff, Ranch Manager, Nutrition Program staff
Plan pipe ceremony for November (TBC with first harvest) with Elder Coordinator, School Staff and Ranch Manager, and School Division Staff
Invite Environmental Health Office to summarize food safety around harvest, field dressing, butchering, packaging, processing and including transportation and food storage and tracking.
Plan snacks and hot drinks to offer at each harvest
Plan a lunch to occur to feed students following morning harvests and prior to travel back to home communities
Secure dates with all interested additional schools for their harvests (2025 - 5 harvests)
Work with local and regional butcher shops for transport and meat processing and packaging for those schools that are not making their own arrangements
Invite all schools to offer food literacy curricular connections before, during and after buffalo harvest
Invite all schools to include preparations for elders, knowledge keepers, experts and the passing on of important ceremony, prayers, or protocols and to invite all relevant participation.
Invite feedback for continuous improvement of the process and revise planning tool based on evaluation
5 | What curricular or community connections do you hope to make?
| Before | During |  |  |  | After
| developing respect for traditional food systems; review community protocols for engaging with Elders respectfully ; Social Studies 10/20/30 & History - Colonization & Food Systems: Understanding the historical destruction of the buffalo and its impact on Indigenous Nations. | Indigenous Studies 10/20/30 - Worldviews & Relationships to Land: Understanding Indigenous relationships with buffalo, food sovereignty, respect for animal life, and sustainable harvesting practices; Cultural Continuity & Revitalization: Exposure to traditional food systems, roles within community, and protocols for harvesting; Reconciliation in Action: Active participation in land-based learning and respectful engagement with Knowledge Keepers/Elders; Science (Biology 30, Science 10/20) Body Systems & Anatomy: Observing musculature, organ systems, and tissue structure during field dressing. Ecology & Sustainability: Examining buffalo as keystone species and their role in prairie ecosystems |  |  |  | English Language Arts 10/20/30 - Reflective & Analytical Writing: Journals, land-based reflection, personal response essays.
6 | Traditional Teachings, Protocols and Practices
Have you involved an elder, knowledge keeper in your planning?
Yes - the school division Elder has assisted with planning and protocols
What are the protocols you will need to follow before, during and after the harvest for your area?
TBD - will update when protocols are finalized
Have you invited an elder, knowledge keeper to the event? (provide name and contact info)
TBD - we would like an Elder at the harvest event as well as at the butchering
Will you need to offer anything to the elder/knowledge keeper when inviting their participation?
tobacco and a small thank you gift for Elder; thank you gift for Ranch/Ranch Manager
7 | What will the seasonal preparations be? *you may want to plan alternative space/activities for outdoor events in case of poor weather
| Location: indoor or outdoor | outdoor - meet at the farm in the driveway
| Time Spent at Location: | arrive 10am; depart 4pm - students to be picked up back at school at 6:30pm
| Expected temperature: | cold; -15 degrees
| Expected Wind: | open farmland, high wind to be expected
| Possible Precipitation: | none in the forecast
| Terrain Considerations: | open farmland, remind students to stay together, watch their step
| Other Considerations: | event will be postponed if weather is inclement
8 | What is the equipment and supplies that you will need and whol will be responsible for bringing that equipment?
| General Supplies | Who to bring? | # needed | Weather Related Supplies | Who to bring? | # needed
| Folding Tables | School | x | Shelter | School | x
| Clean tarps | School | x | Portable Fire | School | x
| Warm Water | Ranch to provide | x | Warm Baselayers | Students | x
| Soap | School | x | Warm Coat | Students/School | TBD
| Garbage Bags | School | x | Warm Ski Pants | Students/School | TBD
| Garbage Cans | School | x | Warm Boots | Students/School | TBD
| Hack Saw/Bone Saw | School/Ranch | x | Blankets | Students/School | TBD
| Skinning Knives | School | x | Hot Paws - hands and feet | School | x
| Other Knives | School | x | Extra Blankets | Division | x
| Mesh Meat Bags | School | x
| Protocols Supplies | Who to bring? | # needed | Other Supplies | Who to bring? | # needed
| Tobacco | Division/Schools | x
| Cloth for Pipe Ceremony | MLTC | x
Student Kit List (what will students need to bring to safely participate):
dress in layers, bring full winter gear if you have it - boots jacket, toque, mitts, scarf, ski pants (if you don't have warm gear, talk to Ms. F, the school has gear you can borrow); water bottle; backpack; snacks and meals will be provided; please leave your electronics at home where they are safe!
9 | Planning for food and beverage needs of participants
| Meals/Snacks |  |  | Who will bring? |  | # of servings required
| Lunch - sandwiches, fruit, bottled water, granola bars, cheese & crackers |  |  | Janet/School to provide |  | 12
| Snacks and Hot Drinks - cocoa, veggies/dip, jerky, tea |  |  | Janet/School to provide |  | 12
| Snacks for the bus ride - bottled water, juice boxes, muffins, |  |  | Ms. F to bring/Division to provide |  | 10
10 | Will accomodation be needed? N/A
Dates accomodation is needed:
Name & Contact Details of Hotel:
Rooming lists:
11 | Who will be attending? *not all activities will require listing individual students, you may choose to simply list the classrooms that are participating
| Students: |  |  | Staff and other Supervisors:
| Name | Grade/Classroom |  | Name |  | Role:
| Sarah C. | 10 |  | Ms. F |  | Lead
| Tony R. | 11 |  | Bruce |  | Supervisor
| Levon R. | 10 |  | Janet |  | Supervisor/Cook
| Emmarae M. | 12 |  | Mr. B |  | Bus Driver
| Aaron B. | 11
Required supervision ratio: 1:15
12 | What other planning has been done?
AFTER THE EVENT
13 | Make note of any successes, challenges, opportunities that you would like to consider for future program planning.

## BLANK VERSION
Land Based Activity Planning Tool
Developed by Meadow Lake Tribal Council Health
1 | Project Name: |  |  | Date(s) of event:
2 | Goal of the Project:
3 | What are the objectives?
4 | Available/Estimated Activity Budget: |  |  |  | Actual Cost:
5 | What are the activities?
6 | What curricular or community connections do you hope to make?
| Before | During |  |  |  | After
7 | Traditional Teachings, Protocols and Practices
Have you involved an elder, knowledge keeper in your planning?
What are the protocols you will need to follow before, during and after the harvest for your area?
Have you invited an elder, knowledge keeper to the event? (provide name and contact info)
Will you need to offer anything to the elder/knowledge keeper when inviting their participation?
8 | What will the seasonal preparations be? *you may want to plan alternative space/activities for outdoor events in case of poor weather
Location: indoor or outdoor
Time Spent at Location:
Expected temperature:
Expected Wind:
Possible Precipitation:
Terrain Considerations:
Other Considerations:
9 | What is the equipment and supplies that you will need and whol will be responsible for bringing that equipment?
| General Supplies | Who to bring? | # needed | Weather Related Supplies | Who to bring? | # needed
| Protocols Supplies | Who to bring? | # needed | Other Supplies | Who to bring? | # needed
Student Kit List (what will students need to bring to safely participate):
10 | Planning for food and beverage needs of participants
| Meals/Snacks |  |  | Who will bring? |  | # of servings required
11 | Will accomodation be needed?
Dates accomodation is needed:
Name & Contact Details of Hotel:
Rooming lists:
12 | Who will be attending? *not all activities will require listing individual students, you may choose to simply list the classrooms that are participating
| Students: |  |  | Staff and other Supervisors:
| Name | Grade/Classroom |  | Name |  | Role:
Required supervision ratio:
13 | What other planning has been done?
AFTER THE EVENT
14 | Make note of any successes, challenges, opportunities that you would like to consider for future program planning.